## Sprint -1
SPRINT-1
ID | User Story | Tasks | Owner | Assigned Date | Due Date | Status | Story Points | Duration
US001 | Track job listings clicked by the user: A Feature that allows the browser extension to keep a record of job listings that a user clicks on while browsing job boards. | Develop click tracking feature | Surbhi | 2023-10-05 | 2023-10-07 | InProgress | 2 | 5hrs
|  | Design database structure for click records | Surbhi | 2023-10-08 | 2023-10-10 | InProgress | 3 | 6hr
|  | Design and implement UI for displaying job listings | Surbhi | 2023-10-11 | 2023-10-15 | InProgress | 4 | 9hrs
US002 | Mark job listings as "Applied": A Feature allowing users to indicate that they have applied for a particular job | Implement UI element for "Applied" button on job listings | Vedanshu | 2023-10-16 | 2023-10-18 | InProgress | 4 | 10hrs
|  | Write code to handle updating job status in the database | Vedanshu | 2023-10-19 | 2023-10-22 | InComplete | 8 | 9hrs
|  | Develop database queries to update job status | Vedanshu | 2023-10-23 | 2023-10-25 | InComplete | 3 | 2hrs
US003 | Implement user authentication: A Feature that ensures only authorized users can access and interact with the browser extension | Create authentication service and define API endpoints | Rahul | 2023-10-23 | 2023-10-25 | InComplete | 8 | 5hrs
|  | Design and implement user registration and login screens | Rahul | 2023-10-26 | 2023-10-28 | InComplete | 6 | 9hrs
|  | Integrate Google Single Sign-On (SSO) for authentication | Rahul | 2023-10-29 | 2023-11-01 | InComplete | 2 | 2hrs